## Sheet1
Milestone1 | Features ID | Feature Description | Feature Type
08/26/2020 ~ 9/9/2020 | 1 | Map Generator with room | Game (Single player) |  | x
| 2 | Player controlled by keyboard and mouse( only for single player w,a,s,d move, mouse shoot aiming ) | Game (Single player) | 2 | x
| 3 | Using simple disc to render player | Game (Single player) | 1 | x
| 4 | Player able to shoot projectile, projectile is also a simple disc | Game (Single player) | 2 | x
| 5 | Player has HP and damage | Game (Single player) | 1 | !
| 6 | Player has basic physics. Pushed by wall and detected when get shot | Game (Single player) | 1 | x
| 7 | Simple AI for enemy | Game (Single player) | 2 | x
| 8 | Items and world cues | Game (Single player) | 1 | x
| 13 | camera position lock(No window) | Camera window |  | x
| 14 | Debug Camera window( AABB ) | Camera window |  | x
| 15 | Player position always inside the camera window | Camera window |  | x
| 16 | When Player trys to leave window, camera follow the player position | Camera window |  | x
| 17 | Window is tweakable in size | Camera window |  | x
| 18 | Debug Window info | Camera window |  | x
Milestone2 | Features ID | Feature Description | Feature Type
2020-09-23 | 19 | Fix camera drift within camera window | Camera snapping |  | x
| 20 | Position-snapping( constantly reduce window drift by focusing the camera back on player | Camera snapping |  | x
| 21 | Horizontal position lock (camera always focus on player horizontally) | Camera snapping |  | x
| 22 | Vertical position lock (camera always focus on player vertically) | Camera snapping |  | x
| 23 | Debug camera snapping info | Camera snapping |  | x
| 24 | Asymptotic position lerp(camera pos is asymptotic lerp between current pos and goal pos) | Camera motion smoothing |  | x
| 25 | Speedup-push-zone (when inside the push-zone, gradually accelerate the camera to catch up with player’s speed) | Camera motion smoothing |  | x
| 26 | Debug camera motion smoothing info | Camera motion smoothing |  | x
| 27 | Camera shake using trauma( relation between trauma and shake intensity is non-linear ) | Camera shake |  | x
| 28 | Positional shake( shake only change the camera position ) | Camera shake |  | x
| 29 | Rotational shake( shake only change the camera orientation ) | Camera shake |  | x
| 30 | blend-shake( shake change both position and orientation ) | Camera shake |  | x
| 31 | Forward-focus( focus on player moving direction ) | Camera Framing |  | x
Milestone3 | Features ID | Feature Description | Feature Type
2020-10-07 | 32 | Projectile-focus( focus on player aiming direction ) | Camera Framing |  | x
| 33 | Cue-focus( focus on game world cues, like item ) | Camera Framing |  | x
| 34 | Blend-focus( blending three focus strategy in different weight) | Camera framing |  | x
| 35 | Debug framing info | Camera framing |  | x
| 11 | Multiple Players generation and destroy ( 1 ~ 4 players ) | Game (Multiple player) |  | x!
| 9 | Simple AI for other player when in single player mode | Game (Multiple player) |  | x
Milestone4 | Features ID | Feature Description | Feature Type
2020-10-21 | 10 | Player controlled by controller( only for multiplayer ) | Game (Multiple player) |  | x
| 12 | enable to shift control to other player | Game (Multiple player) |  | x
| 36 | Zoom to fit( zoom in and zoom out to fit the players positions ) | No split screen |  | x
| 37 | Force on screen( kill player or teleport ) | No split screen |  | x
| 38 | Camera window box for multiplayer | No split screen |  | d
| 39 | Camera snapping for multiplayer | No split screen |  | d
| 40 | Camera motion smoothing for multiplayer | No split screen |  | d
| 41 | Camera framing for multiplayer | No split screen |  | d
| 42 | Camera shake for multiplayer | No split screen |  | d
Milestone5 | Features ID | Feature Description | Feature Type
2020-11-04 | 43 | Each split screen is one axis aligned box | Axis aligned dynamic split screen |  | x
| 44 | Area and shape of split screen is tweakable base on player position | Axis aligned dynamic split screen |  | !
| 45 | Splitting and merging decided real time and smoothly interpolated | Axis aligned dynamic split screen |  | !
| 46 | Camera window box for multiplayer and multicamera | Axis aligned dynamic split screen |  | x
| 47 | Camera snapping for multiplayer and multicamera | Axis aligned dynamic split screen |  | x
| 48 | Camera motion smoothing for multiplayer and multicamera | Axis aligned dynamic split screen |  | x
| 49 | Camera framing for multiplayer and multicamera | Axis aligned dynamic split screen |  | !
| 50 | Camera shake for multiplayer and multicamera | Axis aligned dynamic split screen |  | !
Milestone6 | Features ID | Feature Description | Feature Type
2020-11-18 | 51 | Each split screen is one Voronoi polygon | Voronoi dynamic split screen
| 52 | Area and shape of split screen is tweakable base on player position | Voronoi dynamic split screen
| 53 | splitting edge width and splitting speed is tweakable | Voronoi dynamic split screen
| 54 | Splitting and merging decided real time and smoothly interpolated | Voronoi dynamic split screen
| 55 | Recenter and Reassign the area of each Voronoi split screen | Voronoi dynamic split screen
| 56 | Camera window box for multiplayer and multicamera | Voronoi dynamic split screen
| 57 | Camera snapping for multiplayer and multicamera | Voronoi dynamic split screen
| 58 | Camera motion smoothing for multiplayer and multicamera | Voronoi dynamic split screen
| 59 | Camera framing for multiplayer and multicamera | Voronoi dynamic split screen
| 60 | Camera shake for multiplayer and multicamera | Voronoi dynamic split screen
| 61 | Debug cameras info( position, window box size, etc ) | Camera system
| 62 | Debug split screen strategy | Camera system
Milestone7 | Features ID | Feature Description | Feature Type
2020-12-01 | 63 | Camera system setting for PVP mode | Camera system
| 64 | Camera system setting for PVE mode | Camera system
Winter Break
Milestone1 | Feature ID | Feature | Feature type | Time Expected | Time Actual | Status | Total
2021-02-15 | 9 | 3 player voronoi split | Voronoi Split Screen | 2 | 7 | x | 19
| 10 | 4 player voronoi split | Voronoi Split Screen | 4 | 8 | x
| 11 | Average area voronoi split screen | Voronoi Split Screen | 2 | 2 | !
| 12 | Health based voronoi split screen | Voronoi Split Screen | 2 |  | !
| 13 | voronoi split strategy all split when out of bound | Voronoi Split Screen | 1 | 1 | x
| 14 | voronoi split strategy base on dist between each other | Voronoi Split Screen | 3 |  | !
| 15 | Split edge of the split screen | Voronoi Split Screen | 2 | 1 | x
| 16 | Split and merge feathuring | Voronoi Split Screen | 3 |  | !
Milestone2 | Feature ID | Feature | Feature type | Time Expected | Time Actual |  | Total
2021-03-01 | 11 | Average area voronoi split screen | Voronoi Split Screen | 2 |  | ! | 10
| 12 | Health based voronoi split screen | Voronoi Split Screen | 2
| 14 | voronoi split strategy base on dist between each other | Voronoi Split Screen | 3
| 16 | Split and merge feathuring | Voronoi Split Screen | 3
Milestone3 | Feature ID | Feature | Feature type | Time Expected | Time Actual |  | Total
2021-03-16 | 11 | Average area voronoi split screen | Voronoi Split Screen | 2 | 20 | x | 20
| 12 | Health based voronoi split screen | Voronoi Split Screen | 2 |  | !
| 14 | voronoi split strategy base on dist between each other | Voronoi Split Screen | 3 |  | !
| 16 | Split and merge feathuring | Voronoi Split Screen | 3 |  | !
Milestone4 | Feature ID | Feature | Feature type | Time Expected | Time Actual |  | Total
2021-03-30 | 22 | Build a level for PVP with 4 player | Game play | 5 |  |  | 22
| 23 | Each player able to shoot each other | Game play | 2
| 24 | Each player able to collect items | Game play | 2
| 25 | Static axis aligned box split screen with UI | Game play | 2
| 26 | Vonoroi split screen with UI | Game play | 3
| 27 | Build a level for PVE with 4 player with room and path | Game play | 3
| 28 | Camera framing dynamic base on level design | Game play | 3
| 29 | Enemy Generate when player enter the room | Game play | 2
Milestone5 | Feature ID | Feature | Feature type | Time Expected | Time Actual |  | Total
2021-04-13 | 28 | Final boss fight with three skills | Game play | 6 | 0 |  | 32
| 1 | Screen edge for box | align axis split screen | 2 | 1
| 2 | Dynamic split for 2 players | align axis split screen | 4 | 2
| 32 | imgui UI system for demo | Game play | 2 | 10
| 33 | Merge for two voronoi split screen | Voronoi Split Screen | 1 | 5
| 34 | Merge for three voronoi split screen | Voronoi Split Screen | 1 | 3
| 35 | Merge for four voronoi split screen | Voronoi Split Screen | 1 | 1
| 36 | Game Demo(Axis Aligned split screen) | Game play | 2 | 10
Milestone6 | Feature ID | Feature | Feature type | Time Expected | Time Actual |  | Total
2021-04-26 | 37 | Game Demo(Voronoi Split screen) | Gameplay | 20 |  |  | 50
| 32 | imgui UI system for demo | Game play | 10
| 33 | Merge for two voronoi split screen | Voronoi Split Screen | 10
| 34 | Merge for three voronoi split screen | Voronoi Split Screen | 10

## Sheet2
Features ID | Feature Description | Feature Type
1 | Screen edge for box | align axis split screen
2 | Dynamic split for 2 players | align axis split screen
3 | UI for each players | align axis split screen
4 | Camera window box for multiplayer and multicamera | align axis split screen
5 | Camera snapping for multiplayer and multicamera | align axis split screen
6 | Camera motion smoothing for multiplayer and multicamera | align axis split screen
7 | Camera framing for multiplayer and multicamera | align axis split screen
8 | Camera shake for multiplayer and multicamera | align axis split screen
9 | 3 player voronoi split | Voronoi Split Screen
10 | 4 player voronoi split | Voronoi Split Screen
11 | Average area voronoi split screen | Voronoi Split Screen
12 | Health based voronoi split screen | Voronoi Split Screen
13 | voronoi split strategy all split when out of bound | Voronoi Split Screen
14 | voronoi split strategy base on dist between each other | Voronoi Split Screen
15 | Split edge of the split screen | Voronoi Split Screen
16 | Split and merge gradually | Voronoi Split Screen
17 | Camera window box for multiplayer and multicamera | Voronoi Split Screen
18 | Camera snapping for multiplayer and multicamera | Voronoi Split Screen
19 | Camera motion smoothing for multiplayer and multicamera | Voronoi Split Screen
20 | Camera framing for multiplayer and multicamera | Voronoi Split Screen
21 | Camera shake for multiplayer and multicamera | Voronoi Split Screen
22 | Build a level for PVP with 4 player | Game play
23 | Each player able to shoot each other | Game play
24 | Each player able to collect items | Game play
25 | Static axis aligned box split screen with UI | Game play
26 | Vonoroi split screen with UI | Game play
27 | Build a level for PVE with 4 player with room and path | Game play
28 | Camera framing dynamic base on level design | Game play
29 | Enemy Generate when player enter the room | Game play
28 | Final boss fight with three skills | Game play
30 | Polish | Gameplay
31 | Debug | Gameplay
Additive Feature
32 | imgui UI system for demo | 10
33 | Merge for two voronoi split screen | 5
34 | Merge for three voronoi split screen | 1
35 | Merge for four voronoi split screen | 1
36 | Game Demo(Axis Aligned split screen) | 10
37 | Game Demo(Voronoi Split screen)
38
39
40
41
42
43
44
45
46
47
48